## Phase_Task_Breakdown
Phase | Task Description | Subtasks | Total Hours
A. Project Kickoff & Setup | A.1 Data Ingestion – Load us_disaster_declarations.csv and us_disasters_m5.csv into Power BI, inspect all columns. | Verify encoding, delimiters, import both files Rename columns (remove spaces/special characters) Preview data quality. | 10
B. Data Transformation & Cleaning | B.1 Clean Date & Categorical Fields – Convert and validate dates standardize incident and declaration types. | Convert declaration_date, incident_begin_date, incident_end_date, disaster_closeout_date to Date Handle missing/malformed Standardize state codes, incident_type values Convert program flags to Boolean. | 15
B. Data Transformation & Cleaning | B.2 Validate FIPS & Location – Map FIPS to county names clean designated_area. | Use reference table to map FIPS to county Standardize designated_area text Handle null or mismatched FIPS. | 10
C. Data Modeling & Relationships | C.1 Build Star Schema – Disaster fact table and lookup tables (State, IncidentType, DeclarationType, ProgramTypes). | Create Disaster table with all cleaned columns Create State, IncidentType, DeclarationType, ProgramType lookup tables Establish relationships. | 15
D. DAX Calculations & Measures | D.1 Calculated Fields – DisasterDuration, TimeToDeclaration, Year, Month. | DisasterDuration = DATEDIFF(incident_begin_date, incident_end_date, DAY) TimeToDeclaration = DATEDIFF(incident_begin_date, declaration_date, DAY) Extract Year, Month from declaration_date. | 10
D. DAX Calculations & Measures | D.2 Aggregated Metrics – TotalDisasters, AvgDuration, CountByIncident, CountByProgram, YearlyCount. | Define TotalDisasters = COUNTROWS(Disaster) AvgDuration = AVERAGE(DisasterDuration) CountByIncident = CALCULATE(COUNTROWS, filter by incident_type) etc. | 10
E. Scenario & What-If Analysis | E.1 What-If Parameters – FrequencyAdjustmentPct to project increases in disaster counts ProgramFunding parameter. | Create FrequencyAdjustmentPct using GENERATESERIES ProgramFunding per disaster ProjectedTOTALFunding = [TotalDisasters] * (1 + Adjustment) * [AvgFundingPerDisaster]. | 20
F. Visualization & UX Design | F.1 Build Report Pages – Overview, Geographic Analysis, Temporal Trends, Program Insights, Scenario Insights. | Design KPI cards with TotalDisasters, AvgDuration, Program counts Map of states colored by disaster count Line chart of monthly counts Bar chart of incident vs program Scenario charts. | 30
F. Visualization & UX Design | F.2 Interactivity & Custom Features – Drill-through, tooltips, bookmarks, dynamic slicers. | Drill-through from map to county-level details Tooltip showing incident and program counts Bookmarks for scenario states Slicers for year range, incident type. | 10
G. Testing, QA & Optimization | G.1 DAX Validation & Data Accuracy – Validate measures with sample manual calculations. | Randomly sample 50 records to verify durations, counts Check FIPS mappings Validate scenario outputs. | 10
G. Testing, QA & Optimization | G.2 Performance Tuning – Optimize data model, reduce cardinality in slicers. | Hide unused columns Group rare incident types into “Other” Simplify DAX Limit visuals to top N elements. | 5
H. Documentation & Deployment | H.1 Documentation – User Guide and Technical Document. | User Guide: Data refresh, usage, “What-If” Technical Doc: ERD, DAX formulas, M code steps, update instructions. | 10
H. Documentation & Deployment | H.2 Publish to Power BI Service – Upload .pbix, set permissions, schedule refresh. | Upload to workspace Assign roles Configure monthly refresh Share link with emergency management stakeholders.
I. Team Coordination & Meetings | I.1 Sprint Planning & Stand-ups – Kickoff, weekly stand-ups, mid-sprint review, final demo, retrospective. | Kickoff (2h) Weekly stand-ups (1.5h) Mid-sprint review (2h) Final demo (2h) Retrospective (2.5h). | 10

## Effort_Allocation
Learner | Assignments | Total Hours
L1 | A.1 Data Ingestion (10 h) B.1 Date & Categorical Cleaning (5 h) C.1 Data Model Setup (5 h) D.1 Calculated Fields (5 h) H.1 User Guide (3 h) I.1 Coordination (2 h) | 30
L2 | B.1 Date & Categorical Cleaning (5 h) B.2 FIPS & Location Cleaning (5 h) C.1 Data Model Setup (5 h) D.2 Aggregated Metrics (5 h) F.1 Overview & Geographic visuals (5 h) I.1 Coordination (2 h) | 27
L3 | B.2 FIPS & Location Cleaning (5 h) C.1 Data Model Setup (5 h) D.2 Aggregated Metrics (5 h) E.1 Scenario Setup (10 h) F.1 Temporal & Program visuals (5 h) I.1 Coordination (2 h) | 32
L4 | E.1 Scenario Setup (10 h) F.1 Scenario & Program visuals (10 h) F.2 Interactivity & Tooltips (5 h) G.2 Tuning (3 h) I.1 Coordination (2 h) | 30
L5 | B.1 Date & Categorical Cleaning (5 h) F.1 Feature Analysis & Scenario Insights support (10 h) G.1 DAX Validation (5 h) H.1 Technical Documentation (2 h) I.1 Coordination (2 h) | 24

## Timeline
Week | Milestone/Deliverables
Week 1 | Kickoff: L1 imports both CSVs B.1 & B.2 Cleaning: L1, L2, L5 clean dates, categories, FIPS C.1 Initial Data Model: L1, L2, L3 set up tables.
Week 2 | DAX Calculations: L1, L2, L3 develop duration, aggregated metrics E.1 Scenario Setup: L3, L4 build What-If parameters F.1 UI Skeleton: L2, L3, L4, L5 draft Overview, Geographic, and Temporal pages.
Week 3 | Visualization Refinement: L2, L3, L4 finalize all pages & interactivity G.1 & G.2 Testing & QA: L3, L5 verify measures and optimize Documentation & Publish: L1, L5 finalize guides publish to Power BI Service Final demo & retrospective.

## Key_Deliverables
Deliverable | Details
Cleaned & Transformed Tables | Disaster table with cleaned date fields, categorical fields, and lookup tables for State, IncidentType, DeclarationType, ProgramType.
Star Schema Data Model | Relationships linking Disaster fact table to State, IncidentType, DeclarationType, ProgramType lookup tables.
Calculated Columns & Aggregated Metrics | DisasterDuration, TimeToDeclaration, TotalDisasters, AvgDuration, counts by incident and program, yearly totals.
“What-If” Scenario Measures | FrequencyAdjustmentPct and projected program funding measures based on average cost per disaster.
Power BI .pbix Report | Pages: Overview, Geographic Analysis, Temporal Trends, Program Insights, Scenario Insights with full interactivity.
Documentation | User Guide and Technical Documentation including ERD, DAX formulas, Power Query steps.
Published Workspace | .pbix uploaded to Power BI Service, permissions set, scheduled refresh configured.

## How_to_Use_Plan
Step | Details
Sprint Kickoff (Day 1) | L1 imports both datasets review plan assign roles set up shared folder with CSVs and project docs.
Daily Stand-ups | Each learner reports progress, plans, blockers update project board.
Mid-Sprint Review (End of Week 2) | Demo cleaned data, data model, DAX measures, initial visuals collect feedback.
Final Demo & Handover (End of Week 3) | Present full dashboard walk through documentation publish to Power BI Service confirm scheduled refresh.
Retrospective | Identify successes, challenges, lessons learned document improvements for future iterations.